## 2020 FUW 1st Sem Accomp
Functional Unit Workplan
Period | January to June 2020
Functional Unit | PSTC LAGUNA
|  |  |  | Staff Assigned | [6 empty] | Q1 AND Q2 Target | Approved Budget | Required Resources | Target Customers | Schedule
BSC Functional Objective | BSC Indicator | Program/Project/Function > Task | Success Indicator | SLC | WGDR | TRS | MCP | JKBB | JLL | RML | Quantity | (Php '000) | equipment & materials | internal and external | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total Accomp | Status | % Accomplishment
| Functional Objective I | [13 empty] | Schedule Jan: input number of actual accomplishment; Schedule Jul: input number of actual accomplishment | AS OF JUNE 2020
CUSTOMER PERSPECTIVE A. Promote adoption/utilization of technologies from publicly funded R&D | Technologies promoted, technologies adopted, technology adaptors, product commercialized | -conduct trainings, seminars, and FOR A -Facilitate signing of MOU with starbooks beneficiares - promotion during meetings/conference/workshops | 19 technologies promoted | X | X | X | X | X | X |  | 8 |  | computer, internet connection, phone, office supplies, vehicle | -MSMEs, associations, cooperative, LGUs, Academe, SUCs, NGOs, NGAs, Private Sectors, | Schedule Jan: 1; Schedule Apr: 4; Schedule Jun: 2 | 7 |  | 87.5%
|  |  | 18 technologies adopted | X | X | X | X | X | X |  | 7 |  |  |  | Schedule Jan: 1; Schedule Apr: 4; Schedule Jun: 2 | 7 |  | 100%
|  |  | 18 technology adaptors | X | X | X | X | X | X |  | 7 |  |  |  | Schedule Jan: 1; Schedule Mar: 3; Schedule Jun: 2 | 6 |  | 85.71%
|  |  | 1 product commercialized | X | X | X | X | X | X
CUSTOMER PERSPECTIVE B. Provide support mechanisms for startups, MSMEs and industries in the region (1.a, 1.b, 4.a, 4.b) | New SETUP and GIA Projects | - conduct of Technology Needs Assesment - proposall submission | 11 SETUP Projects | X |  | X | X |  | X |  | 11 |  | computer, internet, phone, office supplies, vehicle, paper, intenet connection, documents submitted by propents i.e. financial reports, TNA, business regsitrarions, etc. | [13 empty] | 1 |  | 9.091% | bar: Schedule Jun
|  |  | 11 GIA Projects | X | X |  |  | X |  |  | 11 |  |  |  | Schedule Feb: 2 | 2 |  | 18.18%
| SETUP technology interventions for SETUP and GIA | - submission of TNA Report - submission of project proposal - facilitate liquiadation report - facilitate fund release - conduct of trainings, for a - provision of consultancy services i.e. CP, EA, MPEX, FST - package design development | 79 SETUP Interventions | X |  | X | X |  | X |  | 38 |  | computer, internet connection, phone, office supplies, vehicle |  | Schedule Feb: 27; Schedule Mar: 1; Schedule Jun: 2 | 30 |  | 78.95%
|  |  | 61 GIA Interventions | X | X |  |  | X |  |  | 30 |  |  |  | Schedule Jan: 1; Schedule Feb: 3; Schedule Mar: 2; Schedule Jun: 2 | 8 |  | 26.67%
| SETUP and GIA customers assisted | - provide technical assistance to MSMEs and Copperatives/people organizations - conduct of trainings/seminars/for a - S & T information referral for walk in clients | 118 SETUP Customers | X |  | X | X |  | X |  | 21 |  |  |  | Schedule Feb: 2; Schedule Mar: 3; Schedule Jun: 9 | 14 |  | 66.67%
|  |  | 119 GIA Customers | X | X |  |  | X |  |  | 61 |  |  |  | Schedule Feb: 9; Schedule Mar: 14; Schedule Jun: 13 | 36 |  | 59.02%
| Consultancy services, trainings/seminar and FOR A | -meetings/on site visit to identified beneficiaries - coordination with SETUP RPMO regarding site visits - progress report monitoring | 3 MPEX, 3 CP, 3 EA, 1 FST | X | X | X | X | X | X |  |  |  | paper, computer, printer, internet connection, phone, vehicle, training materials, projector
| Innovation centers established / maintain | Maintenance / monitoring | CFOSH | X | X | [21 empty] | 1 |  | #DIV/0!
CUSTOMER PERSPECTIVE D. Establish and promote innovation hubs and other similar mechanisms. |  |  | IDD Lab | X |  |  | X | [19 empty] | 1 |  | #DIV/0!
|  |  | Food Innovation Center | X |  |  |  | X | [18 empty] | 1 |  | #DIV/0!
| S & T promotional activities conducted | - facilitate interview i.e. thru radio, tv, press conference etc. | 2 S & T promotional activity (interview woth DOSTv featuring successful SETUP and GIA proponents | X | X | X | X | X | X |  |  |  | computer,internet connection, phone, vehicle
CUSTOMER PERSPECTIVE E. Foster STI Culture | Calibration services renderd by RML, customers assisted 90% of testing/calibation services delivered within agreed time | - conduct on-site calibration services - assist walk-in clients | 3,177 calibration services | X | [5 empty] | X | 1151 |  | tools/equipment for calibration, vehicle, computer, internet connection, office supplies |  | Schedule Jan: 244; Schedule Feb: 266; Schedule Mar: 87; Schedule Apr: 87; Schedule Jun: 142 | 826 |  | 71.76%
CUSTOMER PERSPECTIVE G. Strengthen Regional Standards and Testing Laboratory services | Networks and linkages to other agencies, NGOs, SUCs, Gos, LGUs and Academe and Private Sector | - attend meetings/conferences/seminars/other activities - conduct of FOR A for info dissemination | 51 networks and linkages | X | X | X | X | X | X |  | 23 |  | computer,internet connection, phone, vehicle |  | Schedule Feb: 2; Schedule Mar: 20; Schedule Apr: 2; Schedule May: 21; Schedule Jun: 8 | 53 |  | 230.4%
CUSTOMER PERSPECTIVE K. Other Priority Areas | Functional Objective II
| To provide monthly accomplishment report based on performance indicators on the last Friday of the month | -consolidation/generation of reports | 12 monthly accomplishment report submitted on specified time | X |  |  | X |  | X |  | 6 |  | reports, paper, computer, printer, internet connection | [13 empty] | 6 |  | 100% | bar: Schedule Jan to Schedule Dec
| Functional Objective III | [12 empty] | Regional Office (Planning)
| To provide Quarterly Status Report of SETUP and GIA projects on the last Friday of January, April, July and October | - project monitoring of on-going projects SETUP and GIA - CBP - conduct of on-site vist - phone calls/email - encoding in impression | SETUP - 28 on going projects | X |  |  | X |  | X |  | 56 |  | reports, paper, computer, printer, phone, internet connection |  | Schedule Jan: 27; Schedule Apr: 20 | 47 |  | 83.93%
|  |  | GIA - 26 on going projects per quarter | X |  |  |  | X |  |  | 62 |  |  | Regional Office (SETUP-RPMO) | Schedule Jan: 22; Schedule Apr: 20 | 42 |  | 67.74%
Functional Objective IV
| To submit comprehensive 2020 Annual Report | -consolidation of reports per program on or before December 15, 2020 | 1 annual report submitted on specified time | X |  | X | [6 empty] | reports, paper, computer, printer, internet connection | bar: Schedule Nov to Schedule Dec
Functional Objective V
| To contribute in the development of STI human resources through assistance in the implementation of DOST Scholarship Program According to RSTHRDC procedures, work instructions and directives from DOST-SEI. | -evaluate scholarship applications and encode in the system and generate test permits. |  | X |  |  | X |  | X |  |  |  | reports, paper, computer, printer, internet connection | Regional Office (Scholarship Unit)
Submitted by:
ENGR. SAMUEL L. CAPERIÑA
Provincial Director - PSTC Laguna